- Overview:

This Terms of Reference (ToR) is for a Consultant Firm (hereinafter “Consultant”) to work with the Social Protection and Jobs team at the World Bank (hereinafter “WB Team”) on an assignment that seeks to promote Kitchen Gardening (KG) and Small Livestock Production (SLP) for strengthened Food and Nutrition Security (FNS) among poor households. Activities of the assignment will comprise: (i) identification and adaptation of KG and SLP models that can be adopted by poor households; (ii) pilot implementation and monitoring of KG and SLP models in 4 locations (2 in urban and 2 in rural) for 140 to 200 households, and (iii) assessment of the pilot, together with recommendations and guidance for scaling up the models.  Contract duration would be 18 months including 12 months for pilot implementation.

- Background:

Despite significant gains in human development, poor nutrition remains a pressing challenge in Bangladesh. Almost a quarter of all children under five are stunted and/or underweight, with outcomes twice as worse in the poorest quintile compared to the richest quintile.  Moreover, the rate of overweight ever married women has increased almost three times (12% to 32%) over a decade while 37% women of reproductive age are anemic. Consumption of more nutritious foods has remained slow: not only are diets poorer at the household level but are even poorer for women and children. This suggests that access to nutritious foods at the household level does not automatically translate into access for women and children. Such nutritional status of women and children have long term implications for cognitive development, adult outcomes, and economic productivity, and can persist into subsequent generations creating an intergenerational cycle of malnutrition and detrimentally impacting individual and population level productivity and economic potential. Under these circumstances, nutrition-sensitive programs can help to protect the assets and welfare of poor people and their investments in the health, nutrition, and development of their children.

Review of evidence from Africa and Asia suggests that KG and SLP interventions have the potential to contribute to improved household nutrition. Research suggests that programs that are gender sensitive, and include nutrition education, counseling, and capital investments, significantly improved the nutritional outcomes, primarily through an improvement in dietary choices as well as a general increase in food consumption.

Considering these, the WB team intends to design and pilot nutrition sensitive, climate resilient and scalable KG and SLP models that can be adopted by poor households in different geographical locations to improve their dietary diversity and increase resilience to meet their own nutritional needs, with a specific focus on women and children. The models will be piloted primarily with the beneficiaries  of the Mother and Child Benefit Programme (MCBP), implemented by the Ministry of Women and Children Affairs (MoWCA) and supported by the World Bank-financed Bangladesh Enhancing Investments and Benefits for Early Years (BEIBEY) Project. Lessons from implementation will be used to potentially scale up the intervention across the country for all MCBP beneficiaries as well as for other social safety net beneficiaries.

- Objective:

The objective of the assignment is to implement simple, adaptable, and sustainable KG and SLP practices among vulnerable households to strengthen their food and nutrition security.

Specific objectives of the assignment are,

- Identify and adapt KG and SLP models that can be adapted by poor households in selected geographical locations based on vulnerability maps, ecological profile, climate sustainability, and local supply chains.

- Build capacity of 140 to 200 beneficiary households in select locations on climate-resilient and nutrition-sensitive KG and SLP models to promote the cultivation and consumption of nutritionally adequate and sustainable diets. This will also include sharing recipes that utilize the produce from KGs and SLPs and are adapted to local taste and culinary style.

- Provide necessary production inputs, including raw materials and trainings, to initiate and ensure effective operation and management of the KG and SLP at selected households and community level.

- Conduct Behavioral Change Counselling (BCC), which encourages production, preparation, and consumption of nutritionally adequate and environmentally sustainable diets by raising awareness about their short- and long-term benefits. Train and engage community volunteers and extension workers to provide counseling, advisory and input support to the beneficiaries.

- Monitor implementation progress and assess effectiveness and outcome of the interventions and make recommendations for refinement and sustainability.

- Scope of Services:

Part 1. Inception:

Inception will involve defining the scope, objectives, stakeholders, locations, process of beneficiary selection, and potential risks of the assignment. Based on the consultation with key stakeholders and review of Project documents and relevant literature, the Consultant will provide detailed activity plan, methodology, and tools including instruments to carry out the assignment.

Deliverables under Part 1 will include an inception report detailing activities and timeline; reporting structure; proposed methodology for adaptation of KG and SLP models, monitoring and evaluation (including M&E framework, methodology, sampling, tools and timeline), beneficiary and location selection, training strategy and plan, and potential constraints and solutions that will be encountered in undertaking the assignment.

Part 2. Identification and adaptation of KG and SLP models:

- Identify locations, beneficiary households and community volunteers: The Consultant will identify two urban/semi-urban low-income settlements from two City Corporation/Municipality areas and two rural locations from two upazilas from rural areas, in consultation with the WB team, based on the World Food Programme Poverty Maps and identify 140 to 200 poor households, that will include at least 50% of the MCBP beneficiaries. The Consultant will group the households in clusters which will act as a local resource to promote KG/SLP for FNS in their community. They will also come up with a process to identify beneficiaries that takes into account ease of clustering and implementation arrangements. The Consultant will also identify community volunteers for each cluster to demonstrate, follow up, motivate, counsel, and link the beneficiaries with extension services.

- Identify and customize KG and SLP models that can be adopted by poor households:  The Consultant will identify KG and SLP models for the target beneficiaries and locations based on the local agroecological dynamics, best practices, and implemented and tested models by government and non-government service providers and research institutes. Following identification of KG and SLP models, the Consultant is expected to adapt the models for different agroecological dimensions, local need and local supply chain, availability of required inputs, sustainability, and space constraints. The adaptation of KG and SLP models will focus on promoting application of climate-smart technologies, which are easy to adopt by the target population, to enable regular supply of safe and affordable nutritious food items around the year that are rich in micronutrients. The identification and adaptation process will be carried out in consultation with relevant national actors, including Bangladesh Agricultural Research Institute (BARI) and Department of Agricultural Extension (DAE) under the Ministry of Agriculture, and Department of Livestock Services (DLS) under the Ministry of Fisheries and Livestock (MoFL), technical experts from WB team, and may require field visits to identify needs and knowledge gaps.

- Identify local services and orient relevant frontline officials on the intervention and establish service linkages:  The Consultant will identify relevant government (i.e, DAE , DLS, and BARI) and non-government services and associated staff at local level in  the selected locations and orient the associated officials  on the activities and BCC messages to promote FNS. The Consultant is also expected to establish service linkages so that the beneficiaries have access to technical advice and locally available agricultural extension services and inputs.

- Develop implementation guidelines for administrators: Based on the design of of KG and SLP models for selected locations, the Consultant will develop implementation guidelines for the administrators that will include, but not be limited, to specifying  mechanisms that guide (i) household selection, training, and monitoring  processes; (ii) space requirement, suitable soil condition, local supply chains, and required inputs; (iii) strategies for engaging and training volunteers and establishing functional linkages with extension services; and (iv) BCC strategy to improve beneficiaries’ dietary and consumptions practices.

- Develop training modules and materials to build capacity of beneficiaries, volunteers and extension workers: Based on the KG and SLP models, the Consultant will develop associated training modules to train the beneficiaries, volunteers, and extension workers. Each module should include key BCC messages to address household FNS knowledge, attitude, and practices with a particular focus on women and children. The Consultant is also expected to develop relevant visual aid such as flipcharts, flyers etc. on KG and SLP that will facilitate step by step training, one on one coaching, courtyard sessions, and campaigns.

- Refine/update implementation manual and training modules based on findings and learning from the action research: The models will be refined based on implementation experience, findings and lessons learnt from the action research (further detail in Part 2, g.) conducted throughout implementation. Accordingly, the implementation manual and training modules and materials will be updated for potential scale up of the models.

Deliverables under Part 2 will include KG and SLP model design, local service mapping, implementation manuals, training modules, and training materials.

Part 3. Pilot implementation, monitoring,  and evaluation of KG and SLP models:

- Build community awareness: The Consultant is expected to conduct community awareness activities in selected locations to sensitize community on the purpose and interventions of the pilot and encourage cooperation and participation.

- Conduct training on KG and SLP for beneficiaries: The Consultant will train the beneficiaries on appropriate KG/SLP model for the respective location. In addition, beneficiaries will be trained on technical know -how on post-harvest loss, food storage, preservation, and safety, food loss/waste reduction, and household FNS. The training will include demonstrations at household clusters as practicum for beneficiaries.

- Conduct training for community volunteers: Community volunteers are expected to assist the field administrators in follow up, supervision, and linking beneficiaries with extension supports.  The Consultant will train selected community volunteers on KG and SP models chosen for the respective location; key messages on FNS; technical knowledge and skills on post-harvest loss, food storage, preservation, and safety, and food loss/waste reduction as well as supportive supervision and coaching techniques to keep the beneficiaries motivated.

- Provide productive inputs to the beneficiaries: The Consultant will provide the beneficiaries with productive inputs, including grow bags, climate-friendly/organic fertilizers, seed/saplings, poultry, small ruminants, and feed, to establish and manage KG/SLP at their homestead.  The Consultant will develop input package that is climate-resilient/climate-smart, location-specific, and easily available and affordable. For KG the package may include but not limited to seed/seedlings/samplings, fence, polythene sheet, water cane, vermi compost materials, Trico derma compost material etc. For SLP the package may include but not limited to small ruminants (chicken, duck), and small livestock (goat, sheep), poultry shed, feed, vitamins, and medication.

- Conduct counselling to improve FNS behavior and practices: The Consultant will engage a front line worker(s) as well as the community volunteers to conduct individual and group counselling at household and community on nutrition, food safety, preparation, adapted recipes using KG/SLP produces, and dietary diversification focusing on women and children’s consumption.

- Conduct monitoring and evaluation: Monitoring and evaluation of the pilot will be conducted following an M&E framework developed by the Consultant approved by the WB team. The Consultant will need to articulate a detailed methodology and approach to undertaking monitoring and evaluation in their proposal and inception report. The framework will guide the regular tracking of activity progress, action research for continuous refinement and output and outcome evaluation.

For monitoring, the Consultant will follow action research approach to make continuous refinement to the implement KG and SLP models. This will help find out whether the beneficiaries have acquired appropriate knowledge and skills from the training and demonstrations, whether they follow the recommended guidelines and reasons behind if they are not following. Based on the findings, the Consultant will identify the action required to improve upon the current interventions, support, and guidelines. Where beneficiaries are practicing recommended guidelines, there should be further enquiry on why they are practicing them. These reasons can be used as lessons to other beneficiaries, and they will be incorporated in the training.

For evaluation the Consultant will conduct baseline and endline surveys according to the agreed upon M&E framework. Evaluation will be conducted to understand changes in knowledge, attitude, and practice on nutrition; availability and access to healthy foods; diets and consumption; children’s anthropometry, and women’s empowerment and mental health. Findings from implementation will form the basis of policy dialogue with relevant government counterparts and recommendation and guidance for scaling up. The Consultant will need to articulate a detailed methodology and approach to undertaking this evaluation in their proposal and evaluation plan.

- Prepare a policy brief and case studies: The Consultant is expected to prepare a policy brief to present the challenges and risks of FNS among low-income households with young children, how KG/SLP interventions can contribute to improved FNS and highlight policy options and recommendations. The Consultant is also expected to formulate case studies on success stories and best practices.

Deliverables under Part 3 will include regular progress monitoring reports including findings and lessons learned from action research and recommendations, baseline and endline evaluation reports, policy brief, case studies, and any other knowledge products as required by the WB team.

- Deliverables and Timeline

Timeframe: 18 months including 12 months for field implementation.

Tentative start date: November 2024.

|  | Deliverables | Timeline | Share of Contract Value |
| --- | --- | --- | --- |
|  | Inception | 1 month |  |
| 1 | Inception report detailing activities and timeline; reporting structure; proposed methodology for adaptation of KG and SLP models, monitoring and evaluation (including M&E framework, methodology, sampling, tools and timeline), beneficiary and location selection, training, and potential constraints and solutions that will be encountered in undertaking the assignment. | Within 4 weeks of contract signing | 10% |
| 2 | Identification and adaptation of KG and SLP models | 2 months |  |
| 2.1 | Implementation guidelines for administrators and training modules on KG and SLP models in Bangla and English | Within 8 weeks following the approval of deliverable 1.1 | 10% |
| 2.2 | Final model design, refined implementation guidelines and associated training modules on KG and SLP models in Bangla and English | Within 4 weeks following the submission of implementation completion report (deliverable no. 3.3) | 10% |
| 3 | Pilot implementation, monitoring, and evaluation | 15 months |  |
| 3.1 | Baseline report and presentation | Within 8 weeks following the approval of deliverable 1.1 | 15% |
| 3.2 | Quarterly implementation progress reports (4 reports) | Within 2 weeks following completion of each quarter during implementation | 20% (5% for each report) |
| 3.3 | Implementation completion report including key findings, lessons learned from monitoring and action research and recommendations for refinement and sustainability of the interventions | Within 4 weeks following the completion of the pilot | 15% |
| 3.4 | Endline evaluation report, presentation with key recommendations and guidance for scaling up the interventions through MCBP and /or other social protection programs in the country | Within 6 weeks following completion of the pilot | 15% |
| 3.5 | A Policy brief and case studies | Within 6 weeks following the completion of the pilot | 5% |

Each deliverable shall be submitted to World Bank and will be reviewed and approved by the relevant Task Team Leader (TTL) if the following requirements are met:

- The Deliverables must be submitted in time, according to the table above.

- Reports shall be written in clear and concise language. The body of the report must detail the rationale behind conclusions and recommendations.

- Deliverables must be precise, technically correct, and free of grammatical and mistyping errors.

- The Consultant must provide preliminary drafts with the World Bank team for comments.

- The deliverables should be made available in English in both electronic and paper form. Electronic versions must be editable.

- Electronic files shall be readable without restrictions. If some parts of files should be locked to avoid unintended modifications or to protect key parameters/calculations, the passwords/permits should be provided to World Bank.

- Experience and Skill Sets Expected of the Consultant (Firm):

The Consultant should be able to demonstrate the following capacities at the minimum:

- A at least eight (08) years of relevant experience in designing, implementing, and evaluating projects on promoting food and nutrition security through agricultural and livestock interventions in Bangladesh and/or the South Asia region.

- Demonstrated capabilities in providing technical assistance, especially relating to implementation of nutrition-sensitive agriculture and livestock production extension and BCC programs.

- Strong capacity and experience in conducting action research, project outcome assessment, analyzing qualitative and quantitative data and generating high quality reports in related field, including experience developing data collection instruments measuring household food production, consumption, food nutrition security, and nutritional outcomes for women and children.

- Demonstrated ability to prepare and present comprehensive reports, policy brief and case stories.

- Strong coordination, facilitation, and engagement skills with strong interpersonal communication ability to initiate discussions among different participants.

- Excellent written and spoken fluency in English and Bangla.

- Demonstrated internal capacities applicable to the assignment. Such capacities shall, among others, include a team of professionals with the relevant expertise and experience to implement the required activities.

The Consultant shall ensure that the team is adequately staffed and possesses the necessary skills and experience to effectively carry out the assignment. List of key personnel with their required qualification is given in the below table:

| Key Staff | Academic Qualification | Experience |
| --- | --- | --- |
| Team Leader (Project Manager) | At least a post-graduate degree (master's degree) in Food Security and Nutrition, Agriculture Development, Agronomy, Agricultural Economics, Agriculture Extension, Project Management, Rural Development, Development Economics or related fields from a recognized institution; | - At least 10-12 years of experience working in project management roles with at least 5 years in positions related to agriculture and/or livestock development. - Experience in working with the government and donor-funded projects in the areas of food security and nutrition is an added advantage; - Good understanding of food security and nutrition related issues. - Proven ability to work effectively with a team of individuals from diverse backgrounds. - Strong oral and written communication skills. - Excellent planning, organizational, multi-tasking and time management skills. - Government relations and knowledge of community-driven development issues are added advantages. |
| - Food and Nutrition Security Specialist | At least an undergraduate degree in Food Security and Nutrition, Food Science and Technology, Nutrition Sensitive Agriculture or related field from a recognized institution; | - At least 5 years of practical experience in food and nutrition security, particularly in nutrition sensitive agriculture and food security program management; - Good knowledge of policy developments in the global agriculture and food security areas as well as a good understanding of the needs and challenges limiting the attainment of food security among women and children from vulnerable households in Bangladesh. - Experience in designing and implementing food security and nutrition improvement programs including provision of nutrition education and nutrition sensitive agriculture training programs. |
| - Agronomist or Agricultural Extension Specialist | Advanced university degree Agriculture, Crop Science, Agronomy, Agricultural Extension or related field from a recognized institution; | - At least 5 years of practical experience in the area of agriculture development, agronomy, crop production and farming system research, particularly in the area of crop production and agriculture extension service delivery; - Demonstrated experience in providing agriculture extension and advisory support to vulnerable households, especially in relations to food security and nutrition improvement and nutrition sensitive agriculture. - Good technical knowledge of and experience with homestead gardens development and nutrition behaviour change in Bangladesh. - Experience in developing/adapting implementation manuals, training modules, user guides, and training and coaching of volunteers, agricultural extension staff. |
| Livestock Specialist | Advanced university degree in Animal Science, Veterinary Science, Agriculture, or a relevant field. | - At least 5 years of relevant experience in livestock sector. - Good technical knowledge of and experience with small livestock production at poor households and nutrition behavior change in Bangladesh. - Experience in developing/adapting implementation manual, training modules, user guides, and training and coaching of volunteers, agricultural extension staff |
| Field officer | At least graduate degree in Agriculture, Horticulture or relevant field . | - At least 3 years of work experience in implementation of similar projects/interventions - Proven experience in organizing and coordinating beneficiary training, demonstration; engaging, capacity building and managing of volunteers; collaborating with stakeholders and supervision of field activities |
| Monitoring and Evaluation Specialist | At least post-graduate degree in Economics/Statistics/Social Science or any other equivalent discipline form a reputed university. | - At least 10 years of relevant professional experience which should include demonstrated capacity in action research, evaluation of project efficiency and outcome and development of evaluation tools. - 5 years of experience in monitoring and evaluation of food and nutrition security programs |
| Reporting and Communication expert | At least Graduate degree in Communication or any other equivalent discipline form a reputed university | At least 5 years professional experience in communication which should include report writing, preparing policy notes and case studies focusing on Food and Nutrition Security of vulnerable households. |

- Data Ownership and Data Privacy

The complete work under this assignment will be the property of the World Bank including data, reports, implementation documentation and manuals, and other materials. No data or other information from this assignment will be released to third parties without the written approval of the World Bank team. The Consultant will protect the confidentiality of those participating in the surveys at all stages. All the work conducted is to be treated as confidential. The Consultant must abide by the World Bank’s data privacy policy and  protect the confidentiality of responding individuals and establishments participating in the data collection at all stages.

- Supervision

The Consultant will report to the World Bank Task Team Leaders (TTL), Aneeka Rahman, Senior Social Protection Economist, and Zaineb Majoka, Social Protection Economist.

- Other Information

The Consultant should note that it is responsible for all tax obligations to the Government of Bangladesh and no exemptions applicable to the World Bank Group are applicable to the Consultant for the purpose of the assignment. The financial proposal must include all remuneration and reimbursable costs, inclusive of all relevant taxes, expected to complete the deliverables.

Bangladesh Demographic and Health Survey 2017-18.

World Bank (2019). https://data.worldbank.org/indicator/SH.ANM.ALLW.ZS?locations=BD

World Bank (2019). Food for Improved Nutrition in Bangladesh.